## Sheet1
Risk ID | Category | RISK DESCRIPTION | LIKELIHOOD 1 – 5 | IMPACT 1 – 5 | RISK SEVERITY SCORE Prob x Impact
R1 | Ecological | If a Cyclone occurs, there will be damage on the collection area, thus no /less collection of fruits can take place | 1 | 2.5 | 2.5
R2 | Ecological | If late rainfall occurs, which causes Droughts in the area, this will have a negative impact on the harvesting fruit | 3 | 2.5 | 7.5
R3 | Ecological | Erosion due to uncontrolled rainwater runoff, exacerbated by new footpaths and inadequate soil management, potentially leading to landscape flooding and restricted access to resource collection areas | 3 | 2.5 | 7.5
R4 | Ecological | Deforestation from tree burning for charcoal and firewood collection, causing soil erosion and environmental degradation | 2 | 5 | 10
R5 | Ecological | Overharvesting of fruits leading to resource depletion and potential collapse of local ecosystems. | 3 | 0.625 | 1.875
R6 | Ecological | Insect outbreaks damaging plant populations and disrupting ecology | 3 | 0.625 | 1.875
R7 | Ecological | Decline in pollinator species reducing plant reproduction and affecting biodiversity | 1 | 1.5625 | 1.5625
R8 | Ecological | Spread of fungal pathogens impairing plant health and yield. | 1 | 1.25 | 1.25
R9 | Ecological | Erosion leading to loss of fertile topsoil and seed reserves, undermining plant regeneration | 2 | 1.25 | 2.5
R10 | Ecological | Wildfires causing habitat destruction and loss of biodiversity. | 2 | 1.25 | 2.5
R11 | Ecological | Non-native species outcompeting local flora, altering ecosystems | 2 | 2.5 | 5
R12 | Ecological | Ecouragement on reserve boundary by slash and burn for agricultral fields contributing to deforestation and soil degradation. | 2 | 2.5 | 5
R13 | Economic | No demand for wild fruits impacting project viability and economic sustainability | 2 | 5 | 10
R14 | Social | Diminished local engagement threatening project participation and success. | 2 | 2.5 | 5
R15 | Economic | Alternative income opportunities drawing labor away from sustainable collection practices. | 1 | 2.5 | 2.5
R16 | Social | Community discord impairing collaborative efforts and project adoption. | 3 | 2.5 | 7.5
R17 | Political | Lack of Political will leading to insufficient support and regulatory hurdles for project activities | 2 | 2.5 | 5
R18 | Political | Governmental shifts potentially altering policy support and funding for conservation efforts. | 3 | 1.25 | 3.75
R19 | Social | Shift in leadership in community resulting in project discontinuation or restrictions. | 2 | 2.5 | 5
R20 | Economic | Currency devaluation increasing costs and eroding profit | 3 | 1.25 | 3.75
R21 | Economic | Discontinuation of financial support jeopardizing project viability | 2 | 1.25 | 2.5
R22 | Economic | Insufficient capital to meet FairWild certification standards for processing facilities. | 2 | 2.5 | 5
R23 | Economic | Inadequate funding limiting the procurement of essential raw materials | 3 | 1.25 | 3.75
R24 | Economic | High labor expenses impacting operational budgets and pricing | 2 | 1.25 | 2.5
R25 | Economic | Increasing prices for raw materials or other inputs, affecting profitability | 2 | 1.25 | 2.5
R26 | Legal | Legal liabilities arising from non-adherence to food safety regulations during manufacturing. | 2 | 5 | 10
R27 | Legal | Non-compliance with quality standards at collection points leading to negative consequences | 3 | 5 | 15
R28 | Legal | Risk of (delays in) obtaining necessary legal permits for export. | 3 | 1.25 | 3.75
R29 | Operational | Collection vehicle failure disrupting supply chain and delivery schedules, leading to high unexpexted costs | 3 | 0.625 | 1.875
R30 | Legal | Risk of raw material contamination due to inadequate handling or storage at the village level. | 2 | 5 | 10
R31 | Legal | Potential for product contamination during processing, posing legal and health risks. | 2 | 5 | 10
R32 | Operational | Failure to meet quality benchmarks during processing, risking certification and market access. | 2 | 2.5 | 5
R33 | Operational | Shortages or delays in obtaining suitable packaging, affecting product protection and costs | 2 | 1.25 | 2.5
R34 | Operational | Power outages or inconsistent supply leading to production inefficiencies | 3 | 2.5 | 7.5
R36 | Operational | Risk of theft from materials or equipment | 2 | 1.25 | 2.5
R37 | Economic | Unsuccessful harvesting trips leading discontinuation of project participating | 3 | 2.5 | 7.5
R38 | Legal | Collecting from outside of collection area, leading to the Potential for product contamination, thus not following the rules | 3 | 2.5 | 7.5
R39 | Social | Non-trained/ registered people collect fruit that is given to a trained registered collector to sell | 3 | 2.5 | 7.5
R40 | Operational | Procurement of products too expensive to sell through high costs (fuel; time) | 3 | 2.5 | 7.5
R41 | Economic | Market Share Competition; Similar products with lower, Risk of being outcompeted | 2 | 1.25 | 2.5